# Eagle Scout

Leadership Service

Project Workbook

David Lifescout

Scout’s Name

12 Scouting Way  Kennesaw, Ga 30144

Address

(770) 555-9999

Telephone no.

Troop 1

Unit No.

Mountain Lake

District

Atlanta Area

Local Council

Lord Baden-Powell

Unit leader’s name

100 Founders Road  Kennesaw, Ga 30144

Address

(770) 555-1000

Telephone No.

Bill Hillcourt

Unit advancement committee person’s name

312 Green Bar Drive  Kennesaw, Ga 30144

Address

(770) 555-1212

Telephone No.

This document is to be used as an example only.  It is not the only way a project can be written-up.  This example project follows the narrative read at the Mountain Lake district Life-to-Eagle class about David, a Life Scout, as he goes through the process of completing his project

This is my interpretation of what a project write-up should look like.  Your project may not be this large.  You may not have some of the same things needed for your project.  For example, you may not need a fundraiser.

You may look at this example and be overwhelmed. You may say that, you can never create something that looks like this because you do not know how to use a word processor that well or the project write-up is way too big.  Remember two things:

- How does a little pigmy eat an elephant?  One bite at a time. Break the project down into little pieces.  Do each little piece by itself.  Next thing you know, the elephant will be a bunch of bones.

- Content is more important than form.  What is in the project write-up is more important than how it looks.  Although, you need to create something in which you will be proud.  Treat this project write-up as if you were turning it in as a school project to be graded.  Most importantly convey what, how, and when you are doing your project.

This whole process is not meant to be easy.  If it was easy anyone could do it.  Only 2% of scouts earn the rank of Eagle.  If you have come this far that you are reading this document, you are part of that 2% and you will be successful.

Do not despair, success is just around the corner.

Good luck future Eagle Scout.

Yours in Scouting,

Dave Tackett

Scoutmaster Troop 187

Table of Contents

Project Description

Brief Description	2

Project Benefit	2

Project Details

Present Condition	3

Plans/ Drawings/ Designs	3

Materials	4

Supplies	5

Tools	6

Step-byStep Instructions

Car Wash	7

Pre-Assembly of Benches	7

Courtyard Work	12

Financial Plan	13

Schedule	14

Written/Printed Information	14

Helpers / Workers	15

Adult Supervision	17

Work Site	17

Transportation	17

Approval Signatures	18

Carrying out the Project

Hours		19

Materials	19

Changes	20

Final approval signatures	21

Attachments

A – Before pictures	22

B - Location of Benches and Landscaping	23

C - Bench Diagram	24

D - Proposed Calendar	26

E - Car Wash Flyer	31

F – Bench Assembly Flyers	32

G – Church Workday Flyer	33

H – List of Potential Workers	34

I – Detail of Hours for David Lifescout	35

J – Detail of hours worked by others	37

K – Flower Box Design	44

L – Final Location of benches and Flower Box	45

M – Pictures of Project	46

Life Ambition and purpose	47

Project Description

Describe the project you plan to do.

What group will benefit from the project?

Name of religious institution, school or community					Telephone No.

Street Address					City			State	       Zip code

My Project will be of benefit to the group because:

This concept was discussed with my unit leader on		          12/04/00

Date

The project concept was discussed with the following representative of the group that will benefit from the project.

Project Details

Present Condition

Currently no benches exist in the church’s courtyard.  Attached are pictures of the area (Attachment A). Currently there is only the sidewalk and grass in the courtyard.

Plans / Drawings / Designs

Attached is a diagram of the courtyard and the location of the benches and landscaping (Attachment B).

Attached is the plan for building the benches. (Attachment C)

As required by Troop 1, a 3”x5” plaque will be placed on the side of each bench stating the following:

David Lifescout

Troop 1

Eagle Project

Completion Date

Materials

The lumber to build the benches represents the major cost of this project.  All of the items will be purchased from the local home center.

A friend’s father who owns a hardware store is donating most of the other items for the project.

The mulch to be placed around and under the benches and the potting soil needed for planting will be donated by a local company, Nature Products, which handles dirt and other products. Rev. Amen solicited this donation.

The Women’s club of the church has expressed a great interest in this project. They are donating large outdoor pots for the landscaping.  The ladies will be tending to the plants after the project is completed.  Therefore they had a lot of say in what will be planted. All of the plants will be purchased from Fred’s Nursery.  Several nurseries were approached about donations.  The best that could be done was to get a discount from Fred’s.

At the completion of this project, there will be a ceremony in the courtyard of the church to present the area to the congregation.  During this ceremony Thompson Hardware, Nature Products, Fred’s Nursery, and the Women’s Club will be recognized and presented with a plaque.

| Material | Provided By | Total Needed | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| 2x2x8 Pressure treated pine | Purchase | 39 | 1.59 | 62.01 |
| 2x4x8 Pressure treated pine | Purchase | 10 | 3.99 | 39.90 |
| 2x6x8 Pressure treated pine | Purchase | 3 | 6.50 | 19.50 |
| 4x4x8 Pressure treated pine | Purchase | 8 | 12.50 | 100.00 |
| Gallon Redwood Stain | Purchase | 2 | 15.97 | 31.94 |
| Dwarf Japanese Maple tree | Purchase | 4 | 10.00 | 40.00 |
| Azalea | Purchase | 8 | 5.00 | 20.00 |
| Native Hibiscus | Purchase | 4 | 10.00 | 40.00 |
| Total cost of Purchased Materials |  |  |  | 353.35 |
| Box #12x3” Flathead Screws | Tom Thomson | 2 | 3.15 | 6.30 |
| Box 16d Galvanized Finish Nails | Tom Thomson | 2 | 1.29 | 2.58 |
| ¼”x5 ½” Carriage | Tom Thomson | 24 | 0.75 | 18.00 |
| ¼ “ Nuts | Tom Thomson | 24 | 0.25 | 6.00 |
| ¼” Washers | Tom Thomson | 24 | 0.25 | 6.00 |
| Water Proof Glue | Tom Thomson | 1 | 2.89 | 2.89 |
| Concrete (bags) | Tom Thomson | 16 | 3.49 | 55.84 |
| Name Plaque | Fred Lifescout | 8 | 5.00 | 40.00 |
| Yard of Cypress Mulch | Nature Products | 2 | 30.00 | 60.00 |
| Bag of Potting Soil | Nature Products | 6 | 2.50 | 15.00 |
| Large outdoor pots | Women’s Club | 16 | 8.50 | 136.00 |
| Assorted Plants | Women’s Club |  |  | 20.00 |
| Total cost of donated materials |  |  |  | 368.61 |
| Total cost of all materials |  |  |  | 721.96 |

Supplies

By definition of supplies, the paintbrushes should not be included in this list.   In discussions with Frank Lifescout, it was determined to buy really cheap paintbrushes and then throw them away after the project.  Because of this, the paintbrushes will be consumed and not a part of the final project.  Hence the definition of a supply.

Fred Lifescout, Grandfather, wants to participate in the project.  He is an Eagle Scout himself.  It was felt that the best way he could participate was to cook lunch for the workers on the three Saturday workdays.  It cannot be determined at this time what the cost will be.

| Supply | Provided By | Total Needed | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| Box of Plastic Bags | Purchase | 1 | 8.47 | 8.47 |
| Soap for car wash | Purchase | 1 | 1.78 | 1.78 |
| Poster Board for car wash signs | Purchase | 5 | .55 | 2.75 |
| Package of 50 plastic cups | Purchase | 1 | 1.49 | 1.49 |
| Carpenter Pencils | Purchase | 2 | 0.50 | 1.00 |
| Total cost of Purchased Supplies |  |  |  | 10.96 |
| Pack of 2 80 grit sanding belts for belt sander | Tom Thompson | 2 | 4.39 | 8.78 |
| Sheets of 120 grit sand paper | Tom Thompson | 2 | 1.99 | 3.98 |
| 4” Paint Brush | Tom Thompson | 4 | 1.50 | 6.00 |
| 2” Paint Brush | Tom Thompson | 4 | .99 | 4.96 |
| Towels for Car Wash | Youth Group Members |  |  |  |
| Disposable Masks | Tom Thompson | 20 | .50 | 10.00 |
| Lunch for workers on 3 work days | Fred Lifescout |  |  |  |
| Total cost of donated supplies |  |  |  | 33.72 |
| Total cost of all supplies |  |  |  | 44.68 |

Tools

All of the tools for this project will be borrowed.  No tools will need to be rented.  Renting a concrete mixer was discussed, but it was determined that it would be just as easy and more cost effective to mix the concrete in wheel barrels.

| Tool | Provided By | Total Needed |
| --- | --- | --- |
| Miter Box Saw | Tom Thompson | 1 |
| Scroll Saw | Tom Thompson | 1 |
| Hammer | Frank Lifescout Jim Smith Tom Thompson | 8 |
| Post Hole Digger | Tom Thompson Jim Smith | 2 |
| Belt Sander | Tom Thompson John Smith | 2 |
| Shovel | Frank Lifescout John Smith Tom Thompson | 4 |
| Garden Rake | Frank Lifescout John Smith Tom Thompson | 4 |
| Palm Sander | John Smith Tom Thompson | 2 |
| ¼” drill bit | John Smith | 1 |
| Cordless Drill | Frank Lifescout John Smith |  |
| Drill Bit for #12 Screws | Frank Lifescout | 1 |
| Counter sink bit | Frank Lifescout | 1 |
| Phillips Screw bit for cordless drill | Frank Lifescout | 1 |
| Four Foot Level | Frank Lifescout | 1 |
| Wheel Barrel | Frank Lifescout John Smith | 2 |
| Water Hose | Frank Lifescout | 1 |
| Garden Hoe | Frank Lifescout | 1 |
| Router | Frank Lifescout | 1 |
| ¼” Round-over bit for router | Frank Lifescout | 1 |
| Nail Punch | Frank Lifescout | 1 |
| Ratchet and 9/16 socket | Frank Lifescout | 1 |
| Tape Measure | Frank Lifescout | 2 |
| 24” Measuring stick for holes | Make | 2 |
| Water Cooler | Troop | 2 |

Step-by-step instructions

The project will be done in three major phases with multiple steps in each phase

- Car Wash

- Pre-Assembly of benches

- Courtyard work

First the Car Wash will need to be held. Money will be needed to purchase the lumber for this project.  The lumber is the most expensive part of the project. The money being provided by the church will not be enough to cover the cost.

The benches will be pre-cut, the seat portion and base assembled and all component parts stained before they are taken to the work site at the church.  This will lessen the amount of tools and time needed at the church work site.  The benches will not be completely assembled to make transporting them to the work site easier.

Once at the church, the benches will be completely assembled and set in the ground.  After the benches have been set, the area around the benches will be landscaped.

I.  Car Wash

The car wash will be the simplest part of this project.  The youth group at No Creek Baptist Church will do most of the work for this part of the project.

The steps for doing the car wash are:

- Print tickets for car wash

- Distribute car wash tickets to car wash volunteers

- Collect money from ticket sales

- Gather or buy all items needed for car wash

- Give information about car wash to church secretary for church bulletin

- Make posters to advertise car wash

- Wash and dry the cars

II.  Pre-assembly of benches

Pre-assembly will include:

- Dry pressure treated lumber

- Pre-cut lumber for benches

- Sand all components of benches

- Assemble seat portion of benches

- Assemble base frame of benches

- Stain all bench components

- Transport benches to church

A.  Dry pressure treated lumber

Most of the pressure treated lumber on the market today is very wet.  In order to sand and stain this wood, it will have to be dry.  Mr. Thompson will set aside an area in his yard to dry the lumber.  The lumber will have to be stacked in a shaded area with sticks between each layer of wood.  It is estimated the wood will take two weeks to dry.

B.  Pre-cut lumber for benches

Cut all component parts of the benches.

- End Pieces – Part A

- Side Pieces – Part B

- Posts – Part C

- Seat Slats – Part D

- Seat Ends – Part E

- Center Brace – Part F

- Bevel side pieces

a) Cut End pieces to length from 2 x6’s

- Two end pieces are required for each bench.

- Using Miter box, saw one end of 2x6 board square

- Starting at squared end measure and mark 12 ½”

- Re-Measure mark to ensure it is 12 ½”

- Using Miter box, saw cut 2x6 at mark

- Repeat measuring and cutting until 16 end pieces have been cut.

b) Cut side pieces to length from 2x4’s

- Two side pieces are required for each bench

- One 8 foot 2x4 will yield 2 side pieces

- Using Miter box, saw one end of the 2x4  square

- Starting at squared end, measure and mark 42”

- Re-measure mark to ensure it is 42”

- Using Miter box, saw cut 2x4 at mark

- Mark and cut, using remaining portion of 2x4

- Total of 16 side pieces will be needed

c) Cut all 4x4 posts to length.

- Two legs are required for each bench.

- One 8 foot 4x4 will yield 2 legs.

- Using Miter box, saw square one end of the 4X4 post  (cut no more than an inch off the end of the post)

- Starting at squared, end measure and mark 38 ½”

- Re-measure mark to ensure it is 38 ½”

- Using Miter box, saw cut 4x4 at mark

- Mark and cut, using remaining portion of 4x4

- Total of 16 legs will be needed.

d) Cut seat slats from 2x2’s

- Nine 2x2 slats are needed to build the seat of the bench

- One 8 foot 2x2 will yield 2 side pieces

- Using Miter box, saw square one end of the 2x2

- Starting at squared end, measure and mark 45”

- Re-measure mark to ensure it is 45”

- Using Miter box, saw cut 2x2 at mark

- Mark and cut using remaining portion of 2x2

- Total of 72 slats will be needed

e) Cut Seat Ends from 2x2’s

- Two seat ends are required for each bench

- One 8 foot 2x2 will yield 6 seat ends

- Using Miter box, saw square one end of the 2x2

- Starting at squared, end measure and mark 15 ½”

- Re-measure mark to ensure it is 15 ½”

- Using Miter box, saw cut 2x2 at mark

- Mark and cut using remaining portion of 2x2

- Total of 16 side pieces will be needed

f) Cut Center Brace from 2x4’s

- One center brace is required for each bench

- One 8 foot 2x4 will yield 7 center Braces

- Using Miter box, saw square one end of the 2x4

- Starting at squared end measure and mark 12 ½”

- Re-measure mark to ensure it is 12 ½”

- Mark and cut using remaining portion of 2x4

- Total of 8 center braces will be needed

g) Bevel 2x6 x 12 ½” Side pieces

- Each side piece must be beveled as in the diagram (Attachment C) for part labeled “A”

- Place a mark on each end of side piece 3 ½” from the top

- On the edge and from each end below the first marks, mark 4 ½” from end

- Draw a line between the two marks on each side.

- Using a scroll saw, cut along these two lines

C. Sand all components of bench

To give a more professional and clean look, all of the components need to be sanded and the edges eased.  In addition to looking nicer, sanding will somewhat remove the possibility of people getting splinters from the benches.

The center brace labeled “F” in the bench diagram (Attachment C) is the only part that does not need to be sanded.

Important:  Sawdust from pressure treated lumber is toxic.  When sanding the wood, a mask must be worn.

- Using Router and ¼” round-over bit, rout all edges of bench parts.

- Looking at the bench diagram (Attachment C), the edges that are not being routed are edges that butt up against another part of the bench.

- Side where part A meets part B

- Inside edge of part B where it meets part A

- End of seat slats – part D

- Top inside edge of seat ends (part E) where they meet seat slats part D

- Using belt sander and 80 grit belt, sand all surfaces of the wood

- Using palm sander and 120 grit sand paper, sand all surfaces of the wood

D. Assemble seat portion of benches

Each bench seat is constructed using 9 seat slats – part D (2x2 x 45”), 2 seat ends – part E (2x2 x 15 ½”), 3” deck screws and waterproof glue.

- Apply glue to one end of seat slat

- Butt seat slat against inside edge of seat end.  Should form a large “L”

- Using deck screws, screw through seat end into seat slat.

- Wipe off any excess glue.

- Repeat steps 2,3, and 4 on the right side of seat end.

- Put glue on exposed ends of seat slats

- Attach seat end to right side of seat

- Begin attaching 7 other seat slats to the seat. Apply glue to both ends of the slats and then screw with deck screw. There should be a ¼” gap between each slat.

- Wipe off any excess glue.

E. Assemble base frame of benches

Each bench base is constructed using 2 End pieces – part, 2 Sidepieces – part B, a center brace, 3” deck screws and waterproof wood glue.

- Apply waterproof wood glue to left end of  End piece

- Place Side Piece against glued surface.

- Pre-drill two holes through Side piece into End piece.

- Counter sink holes on Side piece.

- Screw in 2 deck screws #12 3” screws.

- Repeat steps 1 – 5 for other three corners.

- Measure the top of each side piece and place a mark at 21”.

- Apply glue to both ends of Center Brace.

- Center the brace on the mark on both sides of the base.

- Pre-drill two holes and counter sink along the mark on both sides of the seat base through the sides and into the brace.

- Screw in 3” deck screws on both sides of the base.

- Wipe off excess glue.

F. Stain all components of bench

The pastor expressed a wish that the benches have a look of red wood.  The benches must also last a long time and be cost effective.  The solution to this was to use pressure treated wood and then stain it with Redwood stain.

Apply two coats of stain to all components of the benches.  This should be done after seat and base have been assembled.

G. Transport benches to courtyard

Once all the benches are stained, they will need to be transported to the church.  They will be stored in an obscure area until they are set in the ground.

III.  Courtyard Work

- Final assembly of benches

- Prep ground where benches are to be placed

- Set benches into the ground

- Landscape area around the benches

A. Final assembly of benches

The seat, base, and legs will be transported to the work at the church.  Final assembly of the benches will be done there.

- Center bench seat over base

- Attach seat to base using 3” deck screws

- Lay base and seat upside down.

- Stand legs next to end pieces of bench

- Tack the legs in place with 1 nail

- Drill two ¼” hole through each end and legs.

- Run carriage bolt from outside and tighten washer and nut on bolt

- Remove temporary nail

B. Prep ground around area where benches are to be placed

Before the benches are placed in the ground, the area must be cleared and leveled.  The area cleared needs to be 6 ft x 3 ft.  If dirt is needed to raise a location, it can be pulled from another location that needs dirt removed.  Each area where the benches are being placed does not have to be perfect, just close.  Mulch will be put around the benches and it will hide a lot of sins.

C. Set benches into ground

After the benches have been completely assembled and the ground prepared, they will be ready to put into the ground.  The top of the bench should be 16” above the ground.  This will cause the legs to be 24” in the ground.  The depth of the holes for the legs can be measured using a 24” measuring stick.

- Set bench in area where it is to be placed.

- Orient bench to proper location.

- Mark center locations of each leg on the ground

- Draw a 10” diameter circle around mark

- Distance between center is 39”

- Adjust circles as needed.

- Using posthole digger, dig 10” hole 24” deep.

- Test depth using 24” measuring stick.

- Once holes are to depth place bench into holes.

- Measure from top of bench to ground, distance should be 16”.  Using 4-foot level, test levelness of bench. Add or remove dirt from hole to adjust height and level.

- Mix concrete in wheel barrel and use full bag for each hole

D. Landscape area around the benches

The week prior to landscaping, some of the ladies from the Women’s club agreed to help pick out and transport the plants needed for the project.

After the benches have been set in the ground and the bushes will be planted in the ground as directed by the ladies of the church.  Then mulch will be put around each bush and bench.

Financial Plan

Total cost of the project excluding donations will be $388.03

The church has agreed to pay $200 towards the cost of the project.

The remaining portion of the project will be paid for from funds raised by doing a car wash.

The car wash will be held in the church parking lot.  Instead of relying on drive-by traffic alone, two things will be done to increase the number of cars that come by to be washed.

First, Rev. Amen has agreed to advertise the car wash in the church bulletin the week before.  Also tickets will be printed up and pre-sold.  Hopefully some of the people that buy tickets will not show up.  The tickets will be easily produced on a home computer.  Members of Troop 1 and friends will help sell the tickets.

If by chance more money is raised than will be needed for the project, the excess money will be donated to a mission fund run by the church.  This was discussed with Rev. Amen, and he liked this idea.

Schedule

Attached is a calendar of the tentative dates for the project workdays.  Also included on this calendar are several milestones for the project.  (Attachment D)

In general the order of events for the project is:

- Project Approval

- Car wash

  - Print car wash tickets

  - Distribute and sell tickets

  - Gather items needed for car wash

  - Make posters

  - Wash Cars

- Pre-Assembly of benches

  - Dry pressure treated lumber

  - Pre-cut lumber for benches

  - Sand all component of benches

  - Assemble seat portion of benches

  - Assemble base frame of benches

  - Stain all bench components

  - Transport bench components

- Courtyard work

  - Final assembly of benches

  - Prep ground where benches are to be placed

  - Set Benches into the ground

  - Landscape area around benches

- Final Approval

Written/Printed Information

The printed materials related to this project are:

- Tickets for car wash

At this time it has not been determined how the ticket will be designed and printed.  A decision will be made later as to whether the tickets will be printed by a printing company or printed on a home computer.  No design currently exists for the tickets.

- Flyers announcing when and where for the workers

  - Car wash flyer  - Attachment E

  - Bench Assembly flyers – Attachment F

  - Church work Days flyer – Attachment G

- Posters for Car wash

As stated earlier, the youth group of No Creek Baptist Church will be doing most of the work for the car wash. They are making the posters that will be used to advertise the car wash on that day.

Helpers / Workers

The workers will be members of Troop 1, members of the youth group at No Creek Baptist Church, and other friends outside of scouting and church. The project will be broken down into three main phases:

- Car Wash

- Pre-Assembly of benches

- Courtyard work

Car wash

As stated earlier, this will be the easiest portion of the project.  The youth group of the church will provide most of the work for the Car Wash.  In fact, they seem very excited and keep asking when the project will be approved.  (It will be approved when this stupid write-up gets done.  The scoutmaster and the committee chairman keep wanting changes.)  Members of Troop 1 also want to help with this portion of the project; they think that there are some really good looking girls in the youth group.

The president of the youth group, Jane Thompson, has agreed to head up the car wash.  She will make sure the flyers are pass out, the posters are made, and that members of the youth group are called and reminded.  The treasurer, John Wilson, has agreed to handle the ticket sales and money collection.  A minimum of 20 people will be needed for the car wash.  One week before the car wash, Jane Thompson will provide a confirmed list of names that will work.

| Action | Individual | No. of workers | Hours per person | Total Hours |
| --- | --- | --- | --- | --- |
| Create and print tickets | David Lifescout | 1 | 2.00 | 2.00 |
| Arrange work force | Jane Thompson | 1 | 4.00 | 4.00 |
| Handle Tickets and money | John Wilson | 1 | 4.50 | 4.50 |
| Ticket Sales | Youth Group members | 20 | 1.00 | 20.00 |
| Posters | Youth Group members | 5 | 1.00 | 5.00 |
| Gather items needed for car wash | Youth Group member | 2 | 0.75 | 1.50 |
| Car wash | Youth Group Members | 20 | 6.0 | 120.00 |
| Total Est. man hours |  |  |  | 157.00 |

Pre-Assembly of Benches

A maximum of 5 or 6 will be needed to do this phase of the project.  Power tools will be involved, so too many workers may cause a safety hazard.

| Action | Individual | No. of workers | Hours per person | Total Hours |
| --- | --- | --- | --- | --- |
| Cut Lumber | Friends & Troop members | 2 | 1.0 | 2.0 |
| Sand all bench components | Friends & Troop members | 4 | 2.5 | 10.0 |
| Assemble Seats | Friends & Troop members | 6 | 2.0 | 12.0 |
| Assemble Base | Friends & Troop members | 6 | 2.0 | 12.0 |
| Stain all bench components | Friends & Troop members | 6 | 1.5 | 9.0 |
| 2nd coat of stain | Friends & Troop members | 6 | 1.0 | 6.0 |
| Transports benches to church | Friends & Troop members | 4 | 1.0 | 4.0 |
| Total Est. man hours |  |  |  | 55.0 |

Courtyard Work

It has been determined that as in the pre-assembly phase, too many people will hamper the project.  Therefore, four teams of three to four  (12 to 16 people) will be involved in the project.  The team leaders have already been approached.

- Jim Smith - Friend

- Bobby Wolher – SPL Troop 1

- David Tonkins – Patrol Leader Troop 1

- Bill Dawson – Troop Guide Troop 1

| Action | Individual | No. of workers | Hours per person | Total Hours |
| --- | --- | --- | --- | --- |
| Final Assembly of Benches | Friends & Troop members | 16 | 2.0 | 32.0 |
| Prep Ground around bench location | Friends & Troop members | 16 | 1.0 | 16.0 |
| Set benches in Ground | Friends & Troop members | 16 | 2.0 | 32.0 |
| Landscape around Benches | Friends & Troop members | 16 | 3.0 | 48.0 |
| Total Est. man hours |  |  |  | 128.0 |

Several people have already expressed an interest in helping with the Pre-assembly and courtyard phases of the project.  Attachment H is a list of names and telephone numbers of these people.

Total Estimated man-hours for project

| Phase | Total Hours |
| --- | --- |
| Car Wash | 157.0 |
| Pre-Assembly | 55.0 |
| Courtyard | 128.0 |
| Total Est. Man hours | 340.0 |

Adult Supervision

Different adults will be involved during each phase of the project.

During the car wash, Rev. Amen, Nate Franklin, and Sissy Blalock will be the supervising adults.  Mr. Franklin and Mrs. Blalock are the church members involved with the church youth group.  Scouting regulations require that at least one supervising adult have Youth Protection training.  This was discussed with Mr. Franklin.  He has agreed to go through the Youth Protection training before the project is to begin.

During the pre-assembly phase, Tom Thompson and Jim Walker will be the supervising adults.  Mr. Thompson is a friend’s father and Mr. Waker is an assistant scoutmaster with Troop 1.

During the courtyard phase of the project several adults will be present.  Rev. Amen just wants to help.  A few of the ladies from the women’s club also want to be present to ensure the plants are handled properly.  Frank Lifescout and Jim Smith will be present as adult representatives of Troop 1.

Work Site

The workers will do all the work at one of two locations.  The benches will be cut, pre-assembled, and stained at Mr. Tom Thompson’s home workshop.  He has most of the tools needed to complete this project.

The car wash needed to raise funds for the project will happen in the parking lot of the church.

All other work, such as final assembly of the benches, placing of benches, and landscaping will be done in the church courtyard.

Fred Lifescout has decided that he will cook for both the car wash and courtyard workdays in an area adjacent to the church courtyard.

Transportation

All work will be done at the two locations listed above.  The workers will be expected to find their own transportation to the work sites.  If a problem should arise, arrangements will be made to get the worker to the needed work site.

Carrying Out the Project

Hours I Spent Working on the Project

Hours I spent: 	Planning the project	34.25

Carrying out the project	86.50

Total hours I spent working on the Project	120.75

For a detail of the above hours see Attachment I

Hours Spent by Scouts, Venturers, or Other Individuals

Working on the Project

For a detail of hours worked by others see Attachment J

Total number of hours peers worked on the project 436

Grand total hours spent by me and other youth on the project. 522.50

Total hours spent by Adults to complete the project 196.75

Materials Required to Complete the Project

A detail list of the materials and supplies used for this project are on page 4 and 5 of this write-up.  The additional materials needed for the project are listed below

| Material | Provided By | Total Needed | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| 2x2x8 Pressure treated pine | Purchase | 3 | 1.59 | 4.77 |
| 4x4x8 Pressure treated pine | Purchase | 25 | 12.50 | 312.50 |
| Gallon Redwood Stain | Purchase | 1 | 15.97 | 15.97 |
| Total cost of Purchased Materials |  |  |  | 333.24 |
| 5” galvanized spikes | Thompson Hardware | 49 | .55 | 26.95 |
| Yard of top soil | Nature Products | 1 | 26.00 | 26.00 |
| Flowers for Flower Box | Women’s Club |  |  | 62.00 |
| Total cost of Donated Materials |  |  |  | 114.95 |

Changes

Due to the many changes required by my Scoutmaster and Committee Chairman during the project-planning phase, there were only two changes required in execution of the project.  Their questions and comments forced more prior planning for the project than had initially been done.

First the seat assembly took one session longer than was estimated.  This was caused when the first seat top was assembled.  Holes were not pre-drilled on the first seat.  When the deck screws were screwed in, the 2x2’s split.  Due to this additional 2x2’s were purchased.  The step by step instructions for assembling the seats should be changed to include a step for pre-drilling holes for the screws, especially in the 2x2’s.

The church required the second change to the project.  On the first church workday the areas were being prepared to set the benches.  One of the church board members noticed that a bench was being set near the door on left side of the courtyard.  The board held a quick meeting and they asked the bench not be placed at that location. The Women’s club still wanted something at this location so it was decided to put a 4ftx8ft here. The Women’s club would provide the flowers for the box, and Rev. Amen would arrange for the soil needed to fill the box.  It was also decided the cost of the additional lumber necessary for the flower box would come from the money earned for the project. Mr. Thompson agreed to provide the spikes needed to assemble the box.  The design of the flower box and the step-by-step instructions required to build it are shown in

attachment K.  The final location of the flower box and all benches are shown in attachment L.

During the discussion about the unwanted bench, the question was raised of what to do with it.  One of the board members happens to be the principal of Fleur-de-lis Elementary School.  She asked that the bench be put at the mid-point of the school’s nature trail.  She agreed to mark the location on the trail the next week.  A day was later scheduled to set the bench in the ground.

One final note about the project.  The car wash used to fund this project earned more money than was required to complete it.

Car wash	$675.00

Provided by Church	200.00

Total Money Earned or donated	$875.00

Purchased Materials	$ 10.96

Purchased Supplies	353.35

Additional 2x2’s	4.77

Flower Box Supplies

25 4x4’s	312.50

Gallon of stain	15.97

Total cost of materials and supplies	$697.55

##### Money turned over to mission fund on behalf of youth group	$152.45

All expenses were exactly as planned.  No sales taxes were paid because the church’s tax-exempt number was used for all purchases.

After Photographs

See Attachment M for pictures of the project in progress and at completion.

Approvals for Completed Project

Start Date of Project  2/24/01  Completion date of Project 5/13/01

This project was started and has been completed since I received the Life Scout rank, and is respectfully submitted for consideration

5/20/01

_______________________________________________	_________________

Applicant’s Signature								Date

The project was planned, developed, and carried out by the candidate

5/20/01

_______________________________________________	_________________

Signature of Scoutmaster/Coach/Advisor						Date

5/13/01

_______________________________________________	_________________

Signature of representative of religious institution, school, or community			Date

Attachment A – Pictures of the Church Courtyard before Project

Attachment B – Location of Benches and Landscaping

Attachment C – Bench Plans and Material List

Attachment C – Continued

| Item | Name | Dimensions | Quantity |
| --- | --- | --- | --- |
| A | End | 1 ½” x 5 ½” x 12 ½ “ | 2 |
| B | Side | 1 ½” x 3 ½” x 42” | 2 |
| C | Post | 3 ½” x 3 ½” x 38 ½ “ | 2 |
| D | Seat Slat | 1 ½” x 1 ½” x 45 | 9 |
| E | Seat End | 1 ½” x 1 ½” x 15 ½” | 2 |
| F | Center Brace | 1 ½” x 5 ½” x 12 ½ “ | 1 |
|  | Deck screws | No. 12 x 3” |  |
|  | Carriage Bolt with nut and washer | ¼” x 5 ½” | 4 |

Attachment D – Proposed Calendar

Following is a proposed calendar of events for the Eagle project.  It contains all milestone dates for the project.  All workdays are noted, as well as personal objectives for completing the project.

#### Proposed Calendar for Eagle Project

###### Proposed Calendar for Eagle Project

###### Proposed Calendar for Eagle Project

###### Proposed Calendar for Eagle Project

Attachment E – Car Wash Flyer

### Attachment F – Bench Assembly Flyers

### Attachment G – Church Work Day Flyer

### Attachment H – List of Potential Workers

For Bench Pre-Assembly and Courtyard Work

| Name | Association | Phone Number | Job |
| --- | --- | --- | --- |
| Youths |  |  |  |
| Jim Smith | Friend | (770) 555-9999 | Courtyard Team leader |
| Bobby Wolher | Troop 1 | (770) 555-9999 | Courtyard Team leader |
| David Tonkins | Troop 1 | (770) 555-9999 | Courtyard Team leader |
| Bill Dawson | Troop 1 | (770) 555-9999 | Courtyard Team leader |
| Rip Torn | Troop 1 | (770) 555-9999 | Bench and Courtyard |
| Buster Anderson | Troop 1 | (770) 555-9999 | Bench and Courtyard |
| Dan Noster | Troop 1 | (770) 555-9999 | Bench and Courtyard |
| Trusty Tommy | Troop 1 | (770) 555-9999 | Bench and Courtyard |
| Willly Wonka | Troop 1 | (770) 555-9999 | Bench and Courtyard |
| William Wallace | Troop 1 | (770) 555-9999 | Courtyard |
| Fran Cunningham | Youth Group | (770) 555-9999 | Courtyard |
| Gail Butters | Youth Group | (770) 555-9999 | Courtyard |
| Adam Pevers | Troop 1 | (770) 555-9999 | Courtyard |
| Frank Foster | Troop 1 | (770) 555-9999 | Courtyard |
| Flash Gordon | Troop 1 | (770) 555-9999 | Courtyard |
| Clark Kent | Troop 1 | (770) 555-9999 | Courtyard |
| Oliver Twist | Troop 1 | (770) 555-9999 | Courtyard |
| Adults |  |  |  |
| Nate Franklin | Youth Group | (770) 555-9999 | Car Wash |
| Sissy Blalock | Youth Group | (770) 555-9999 | Car Wash |
| Bertha Beterthanyou | Women’s Cub | (770) 555-9999 | Courtyard |
| Minie Pearl | Women’s Cub | (770) 555-9999 | Courtyard |
| Lilla Lane | Women’s Cub | (770) 555-9999 | Courtyard |
| Ester Thompson | Women’s Cub | (770) 555-9999 | Courtyard |
| Ward Cleaver | Troop 1 | (770) 555-9999 | Courtyard |

### Attachment I – Detail of hours for David Lifescout

| David Lifescout Planning Hours |  |  |
| --- | --- | --- |
| Date | Task | Hours |
| 1-Dec-00 | Initial Discussions with Rev Amen | 0.50 |
| 4-Dec-00 | Initial Discussions with Scoutmaster | 0.50 |
| 6-Dec-00 | Disc with Rev Amen | 1.50 |
| 10-Dec-00 | Presentation to Church Board | 1.25 |
| 17-Dec-00 | Disc with Women's Group | 2.00 |
| 7-Jan-01 | Disc with youth group leader | 0.25 |
| 14-Jan-01 | Presentation to Youth Group | 0.25 |
| 14-Jan-01 | Search Internet for Bench design and plans | 2.25 |
| 16-Jan-01 | Disc with Fred Lifescout about Food | 0.50 |
| 19-Jan-01 | Disc with Tom Thompson about materials | 0.25 |
| 19-Jan-01 | Project write-up | 1.50 |
| 20-Jan-01 | Determine Material Costs | 2.75 |
| 20-Jan-01 | Project write-up | 2.00 |
| 21-Jan-01 | Project write-up | 2.50 |
| 26-Jan-01 | Project write-up | 3.00 |
| 27-Jan-01 | Project write-up | 4.00 |
| 28-Jan-01 | Final presentation to Church Board | 0.50 |
| 29-Jan-01 | Initial Presentation to Scoutmaster and Committee Chairman | 0.50 |
| 3-Feb-01 | Project write-up | 2.00 |
| 4-Feb-01 | Disc with Rev Amen | 0.75 |
| 4-Feb-01 | Determine Cost of donated Materials | 1.25 |
| 4-Feb-01 | Project write-up | 1.50 |
| 5-Feb-01 | 2nd presentation to Scoutmaster and Committee Chairman | 0.50 |
| 17-Feb-01 | Project write-up | 1.75 |
| 19-Feb-01 | 3rd presentation to Scoutmaster & Committee Chairman | 0.50 |
|  | Total Planning Hours | 34.25 |

Attachment I  – Detail of hours for David Lifescout - Continued

|  | David Lifescout - Hours Carrying Out the Project |  |
| --- | --- | --- |
| Date | Task | Hours |
| 24-Feb-01 | Design and print Car wash tickets | 2.00 |
| 25-Feb-01 | Design and print Car wash tickets | 1.00 |
| 4-Mar-01 | Distribute tickets to sell | 0.50 |
| 4-Mar-01 | Discussions with youth group about car wash | 0.75 |
| 5-Mar-01 | Call church with info on car wash | 0.25 |
| 10-Mar-01 | Gather items need for car wash | 1.50 |
| 14-Mar-01 | Meet with girls from youth group to make posters for car wash | 2.00 |
| 16-Mar-01 | Collect money and tickets from youth group Treasurer | 0.75 |
| 17-Mar-01 | Car Wash | 7.50 |
| 18-Mar-01 | Get lumber and set up to dry | 3.50 |
| 3-Apr-01 | Pre-cut benches & sand components | 3.00 |
| 3-Apr-01 | Sand bench components | 2.50 |
| 10-Apr-01 | Assemble benches | 3.00 |
| 11-Apr-01 | Assemble benches | 3.75 |
| 12-Apr-01 | Assemble benches | 2.50 |
| 17-Apr-01 | Stain benches | 1.50 |
| 18-Apr-01 | Stain benches | 1.00 |
| 21-Apr-01 | Transport benches to church | 2.25 |
| 24-Feb-01 | Purchase and transport flowers and bushes | 2.50 |
| 26-Feb-01 | Purchase and transport final materials and supplies | 2.75 |
| 27-Apr-01 | Gather and transport all needed tools | 3.75 |
| 28-Apr-01 | Final assembly of benches and ground prep | 7.50 |
| 28-Apr-01 | Move one bench to scout hut | 1.00 |
| 29-Apr-01 | Draw up plans for flower box | 0.75 |
| 29-Apr-01 | Purchase material for flower box | 1.25 |
| 5-May-01 | Set benches / Build flower box/ Landscaping | 9.00 |
| 5-May-01 | Review with pastor | 0.75 |
| 12-May-01 | Begin Final write-up of project | 3.00 |
| 13-May-01 | Presentation of project to Church members and thanks to workers | 1.50 |
| 13-May-01 | Final write-up | 1.75 |
| 15-May-01 | Final write-up | 2.00 |
| 19-May-01 | Final write-up | 3.00 |
| 20-May-01 | Final write-up | 1.75 |
|  | Total hours to carry out project | 81.50 |

Attachment J  – Detail of hours worked by others

Youth Detail Hours

| Car Wash |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Task | Name | Organization | Hours |
| 4-Mar | Planning Meeting with Youth Group | Jane Thompson | Youth Group | 0.75 |
|  |  | John Wilson | Youth Group | 0.75 |
|  |  | Paulie Amples | Youth Group | 0.75 |
|  |  | Jill Franks | Youth Group | 0.75 |
|  |  | David Jackson | Youth Group | 0.75 |
| 4-Mar | Distribution of Tickets | John Wilson | Youth Group | 1.00 |
|  |  | Jane Thompson | Youth Group | 1.00 |
|  |  | David Jackson | Youth Group | 1.00 |
| 10-Mar | Gather items need for car wash | Jane Thompson | Youth Group | 1.25 |
|  |  | David Jackson | Youth Group | 1.25 |
| 14-Mar | Make Posters | Jane Thompson | Youth Group | 2.00 |
|  |  | Paulie Amples | Youth Group | 2.00 |
|  |  | Jill Franks | Youth Group | 2.00 |
|  |  | Jodie Banks | Youth Group | 2.00 |
|  |  | Suzi Pile | Youth Group | 2.00 |
| 16-Mar | Collect Money & Tickets | John Wilson | Youth Group | 2.50 |
| 17-Mar | Car Wash | Jane Thompson | Youth Group | 7.50 |
|  |  | John Wilson | Youth Group | 7.50 |
|  |  | Paulie Amples | Youth Group | 6.00 |
|  |  | Jill Franks | Youth Group | 6.00 |
|  |  | Jodie Banks | Youth Group | 6.00 |
|  |  | Suzi Pile | Youth Group | 6.00 |
|  |  | Jim Smith | Friend | 7.50 |
|  |  | Bobby Wohler | Troop 1 | 7.50 |
|  |  | Did David Tonkins | Troop 1 | 6.00 |
|  |  | Bill Dawson | Troop 1 | 7.50 |
|  |  | David Jackson | Youth Group | 6.00 |
|  |  | Joe Banks | Youth Group | 6.00 |
|  |  | Sally Forth | Youth Group | 6.00 |
|  |  | Lindsey Danford | Youth Group | 6.00 |
|  |  | Britney Spears | Youth Group | 6.00 |
|  |  | Willie Coyote | Youth Group | 6.00 |
|  |  | Fran Cunningham | Youth Group | 6.00 |
|  |  | Gail Butters | Youth Group | 6.00 |
|  |  | Nadine Sams | Youth Group | 6.00 |
|  |  | Josh Nelson | Youth Group | 6.00 |
|  |  | Sam Lake | Youth Group | 6.00 |
|  | Total Car Wash Hours | 155.25 |

Attachment J – Detail of hours worked by others-Continued

Peer Detail Hours - Continued

| Bench Assembly |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Task | Name | Organization | Hours |
| 18-Mar-01 | Get lumber and set up to dry | Jim Smith | Friend | 3.50 |
|  |  | Bobby Wohler | Troop 1 | 3.50 |
| 3-Apr-01 | Pre-cut benches & sand components | Rip Torn | Troop 1 | 3.00 |
|  |  | Jim Smith | Friend | 3.00 |
|  |  | Bobby Wohler | Troop 1 | 3.00 |
|  |  | Jane Thompson | Youth Group | 3.00 |
|  |  | Buster Anderson | Troop 1 | 3.00 |
|  |  | Dan Noster | Troop 1 | 3.00 |
| 4-Apr-01 | Sand bench components | Rip Torn | Troop 1 | 2.50 |
|  |  | Jim Smith | Friend | 2.50 |
|  |  | Bobby Wohler | Troop 1 | 2.50 |
|  |  | Jane Thompson | Youth Group | 2.50 |
|  |  | Buster Anderson | Troop 1 | 2.50 |
|  |  | Dan Noster | Troop 1 | 2.50 |
| 10-Apr-01 | Assemble benches | Rip Torn | Troop 1 | 3.00 |
|  |  | Jim Smith | Friend | 3.00 |
|  |  | Bobby Wohler | Troop 1 | 3.00 |
|  |  | Trusty Tommy | Troop 1 | 3.00 |
|  |  | Willy Wonka | Troop 1 | 3.00 |
| 11-Apr-01 | Assemble benches | Rip Torn | Troop 1 | 3.00 |
|  |  | Jim Smith | Friend | 3.00 |
|  |  | Bobby Wohler | Troop 1 | 3.00 |
|  |  | Trusty Tommy | Troop 1 | 3.00 |
|  |  | Willy Wonka | Troop 1 | 3.00 |
|  |  | Dan Noster | Troop 1 | 3.00 |
| 12-Apr-01 | Assemble benches | Rip Torn | Troop 1 | 2.50 |
|  |  | Jim Smith | Friend | 2.50 |
|  |  | Bobby Wohler | Troop 1 | 2.50 |
|  |  | Trusty Tommy | Troop 1 | 2.50 |
|  |  | Willy Wonka | Troop 1 | 2.50 |
|  |  | Dan Noster | Troop 1 | 2.50 |
| 17-Apr-01 | Stain benches | Rip Torn | Troop 1 | 1.50 |
|  |  | Jim Smith | Friend | 1.50 |
|  |  | Bobby Wohler | Troop 1 | 1.50 |
|  |  | Trusty Tommy | Troop 1 | 1.50 |
| 18-Apr-01 | Stain benches | Rip Torn | Troop 1 | 1.00 |
|  |  | Jim Smith | Friend | 1.00 |
|  |  | Bobby Wohler | Troop 1 | 1.00 |
|  |  | Trusty Tommy | Troop 1 | 1.00 |
|  | Total Bench Assembly Hours | 98.00 |

Attachment J  – Detail of hours worked by others-Continued

Peer Detail Hours - Continued

| Date | Task | Name | Organization | Hours |
| --- | --- | --- | --- | --- |
| 21-Apr-01 | Transport benches to church | Jim Smith | Friend | 2.25 |
|  |  | Bobby Wohler | Troop 1 | 2.25 |
| 24-Feb-01 | Purchase and transport flowers and bushes | Jane Thompson | Youth Group | 2.50 |
| 26-Feb-01 | Purchase and transport final materials | Jane Thompson | Youth Group | 2.75 |
|  | and supplies | Jim Smith | Friend | 2.75 |
|  |  | Bobby Wohler | Troop 1 | 2.75 |
| 27-Apr-01 | Gather and transport all needed tools | Jim Smith | Friend | 3.75 |
|  |  | Bobby Wohler | Troop 1 | 3.75 |
| 28-Apr-01 | Final assembly of benches and ground | Jim Smith | Friend | 4.00 |
|  | prep | William Wallace | Troop 1 | 4.00 |
|  |  | Fran Cunningham | Youth Group | 4.00 |
|  |  | Rip Torn | Troop 1 | 4.00 |
|  |  | Bobby Wohler | Troop 1 | 4.00 |
|  |  | Jane Thompson | Youth Group | 4.00 |
|  |  | Buster Anderson | Troop 1 | 4.00 |
|  |  | Dan Noster | Troop 1 | 4.00 |
|  |  | David Tonkins | Troop 1 | 4.00 |
|  |  | Gail Butters | Youth Group | 4.00 |
|  |  | Adam Pevers | Troop 1 | 4.00 |
|  |  | Frank Foster | Troop 1 | 4.00 |
|  |  | Bill Dawson | Troop 1 | 4.00 |
|  |  | Flash Gordon | Troop 1 | 4.00 |
|  |  | Clark Kent | Troop 1 | 4.00 |
|  |  | Oliver Twist | Troop 1 | 4.00 |
| 29-Apr-01 | Purchase material for flower box | Jane Thompson | Youth Group | 1.25 |
|  |  | Bobby Wohler | Troop 1 | 1.25 |
| 1-May-01 | Pre-cut all components of Flower Box - | Jim Smith | Friend | 1.50 |
|  | Apply 1st coat of stain | Bobby Wohler | Troop 1 | 1.50 |
|  |  | Trusty Tommy | Troop 1 | 1.50 |
| 2-May-01 | Apply 2nd coat of stain | Jim Smith | Friend | 1.00 |
|  |  | Bobby Wohler | Troop 1 | 1.00 |
|  |  | Trusty Tommy | Troop 1 | 1.00 |

Attachment J  – Detail of hours worked by others-Continued

Peer Detail Hours - Continued

| Date | Task | Name | Organization | Hours |
| --- | --- | --- | --- | --- |
| 5-May-01 | Set benches / Build flower box/ | Jim Smith | Friend | 5.50 |
|  | Landscaping | William Wallace | Troop 1 | 4.50 |
|  |  | Fran Cunningham | Youth Group | 4.50 |
|  |  | Rip Torn | Troop 1 | 4.50 |
|  |  | Bobby Wohler | Troop 1 | 5.50 |
|  |  | Jane Thompson | Youth Group | 4.50 |
|  |  | Buster Anderson | Troop 1 | 4.50 |
|  |  | Dan Noster | Troop 1 | 4.50 |
|  |  | David Tonkins | Troop 1 | 4.50 |
|  |  | Gail Butters | Youth Group | 4.50 |
|  |  | Adam Pevers | Troop 1 | 3.50 |
|  |  | Frank Foster | Troop 1 | 3.50 |
|  |  | Bill Dawson | Troop 1 | 5.50 |
|  |  | Flash Gordon | Troop 1 | 3.50 |
|  |  | Clark Kent | Troop 1 | 3.50 |
|  |  | Oliver Twist | Troop 1 | 3.50 |
|  | Total Courtyard Hours | 166.75 |
| Other Tasks |  |  |  |  |
| 28-Apr-01 | Transport unused bench to Fleur-de-lis Elementary | Jane Thompson | Youth Group | 1.00 |
| 12-May-01 | Set unused bench at half-way point of | Jim Smith | Friend | 1.50 |
|  | Floure-De-Lee Elementary's nature trail | William Wallace | Troop 1 | 1.50 |
|  |  | Fran Cunningham | Youth Group | 1.50 |
|  |  | Rip Torn | Troop 1 | 1.50 |
| 13-May-01 | Presentation of project to Church | Jane Thompson | Youth Group | 1.50 |
|  | members and thanks to workers | John Wilson | Youth Group | 1.50 |
|  |  | Paulie Amples | Youth Group | 1.50 |
|  |  | Jill Franks | Youth Group | 1.50 |
|  |  | David Jackson | Youth Group | 1.50 |
|  |  | Bobby Wolher | Troop 1 | 1.50 |
|  | Total Other Hours | 16.00 |

Summary of Peer Hours

|  | Actual | Estimated |
| --- | --- | --- |
| Car Wash | 155.25 | 157.00 |
| Bench Assembly | 98.00 | 55.00 |
| Court Yard | 166.75 | 128.00 |
| Other | 16.00 | - |
| Total Project Hours | 436.00 | 340.00 |

Attachment J  – Detail of hours worked by others-Continued

Adult Detail Hours

| Car Wash |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Task | Name | Organization | Hours |
| 4-Mar | Planning Meeting with Youth Group | Rev Ronald Amen | Youth Group | 0.75 |
|  |  | Nate Franklin | Youth Group | 0.75 |
|  |  | Sissy Blalock | Youth Group | 0.75 |
| 14-Mar | Make Posters | Sissy Blalock | Youth Group | 2.00 |
|  |  | Judy Thompson | Youth Group | 2.00 |
| 17-Mar | Car Wash | Fred Lifescout | Grandfather | 7.50 |
|  |  | Rev Ronald Amen | Youth Group | 7.50 |
|  |  | Nate Franklin | Youth Group | 7.50 |
|  |  | Sissy Blalock | Youth Group | 7.50 |
|  | Total Car Wash Hours | 36.25 |
| Bench Assembly |  |  |  |  |
| Date | Task | Name | Organization | Hours |
| 18-Mar-01 | Get lumber and set up to dry | Tom Thompson | Friend | 3.50 |
| 3-Apr-01 | Pre-cut benches & sand components | Tom Thompson | Friend | 3.00 |
|  |  | Jim Walker | Troop 1 | 3.00 |
|  |  | Frank Lifescout | Troop 1 | 3.00 |
| 4-Apr-01 | Sand bench components | Tom Thompson | Friend | 2.50 |
|  |  | Jim Walker | Troop 1 | 2.50 |
|  |  | Frank Lifescout | Troop 1 | 2.50 |
| 10-Apr-01 | Assemble benches | Tom Thompson | Friend | 3.00 |
|  |  | Jim Walker | Troop 1 | 3.00 |
|  |  | Frank Lifescout | Troop 1 | 3.00 |
| 11-Apr-01 | Assemble benches | Tom Thompson | Friend | 3.00 |
|  |  | Jim Walker | Troop 1 | 3.00 |
|  |  | Frank Lifescout | Troop 1 | 3.00 |
| 12-Apr-01 | Assemble benches | Tom Thompson | Friend | 2.50 |
|  |  | Jim Walker | Troop 1 | 2.50 |
|  |  | Frank Lifescout | Troop 1 | 2.50 |
| 17-Apr-01 | Stain benches | Tom Thompson | Friend | 1.50 |
|  |  | Jim Walker | Troop 1 | 1.50 |
| 18-Apr-01 | Stain benches | Tom Thompson | Friend | 1.00 |
|  |  | Jim Walker | Troop 1 | 1.00 |
|  |  | Fred Lifescout | Grandfather | 1.00 |
|  | Total Bench Assembly Hours | 51.50 |

Attachment J  – Detail of hours worked by others-Continued

Adult Detail Hours Continued

| Courtyard Work |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Task | Name | Organization | Hours |
| 21-Apr-01 | Transport benches to church | Tom Thompson | Friend | 2.25 |
| 24-Feb-01 | Purchase and transport flowers and | Bertha Beterthanyou | Women's Club | 2.50 |
|  | bushes | Minie Pearl | Women's Club | 2.50 |
|  |  | Lilla Lane | Women's Club | 2.50 |
|  |  | Ester Thompson | Women's Club | 2.50 |
| 26-Feb-01 | Purchase and transport final materials and supplies | Tom Thompson | Friend | 2.75 |
| 27-Apr-01 | Gather and transport all needed tools | Tom Thompson | Friend | 3.75 |
| 28-Apr-01 | Final assembly of benches and | Tom Thompson | Friend | 4.00 |
|  | ground prep | Rev Ronald Amen | Church | 4.00 |
|  |  | Fred Lifescout | Grandfather | 4.00 |
|  |  | Frank Lifescout | Troop 1 | 4.00 |
|  |  | Jim Walker | Troop 1 | 4.00 |
|  |  | Ward Cleaver | Troop 1 | 4.00 |
|  |  | Bertha Beterthanyou | Women's Club | 2.50 |
|  |  | Minie Pearl | Women's Club | 2.50 |
| 28-Apr-01 | Meeting with Board and Women’s club | Bertha Beterthanyou | Women's Club | 1.00 |
|  | about new flower box and unwanted | Minie Pearl | Women's Club | 1.00 |
|  | bench | Tom Thompson | Friend | 1.00 |
|  |  | Rev Ronald Amen | Church | 1.00 |
| 29-Apr-01 | Purchase material for flower box | Tom Thompson | Friend | 1.25 |
| 1-May-01 | Pre-cut all components of Flower Box - | Tom Thompson | Friend | 1.50 |
|  | Apply 1st coat of stain | Jim Walker | Troop 1 | 1.50 |
|  |  | Fred Lifescout | Grandfather | 1.50 |
| 2-May-01 | Apply 2nd coat of stain | Tom Thompson | Friend | 1.00 |
|  |  | Jim Walker | Troop 1 | 1.00 |
|  |  | Fred Lifescout | Grandfather | 1.00 |
| 5-May-01 | Set benches / Build flower box/ | Tom Thompson | Friend | 5.50 |
|  | Landscaping | Rev Ronald Amen | Church | 5.50 |
|  |  | Fred Lifescout | Grandfather | 5.50 |
|  |  | Frank Lifescout | Troop 1 | 5.50 |
|  |  | Jim Walker | Troop 1 | 4.00 |
|  |  | Ward Cleaver | Troop 1 | 4.00 |
|  |  | Bertha Beterthanyou | Women's Club | 2.75 |
|  |  | Minie Pearl | Women's Club | 2.75 |
|  |  | Lilla Lane | Women's Club | 2.75 |
|  |  | Ester Thompson | Women's Club | 2.75 |
|  | Total Courtyard Hours | 101.50 |

Attachment J  – Detail of hours worked by others-Continued

Adult Detail Hours Continued

| Other Tasks |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Task | Name | Organization | Hours |
| 12-May-01 | Set unused bench at half-way point of Floure-De-Lee Elementary's nature trail | Fred Lifescout | Grandfather | 1.50 |
|  |  | Jim Walker | Troop 1 | 1.50 |
| 13-May-01 | Presentation of project to Church members and thanks to workers | Rev Ronald Amen | Youth Group | 1.50 |
|  |  | Nate Franklin | Youth Group | 1.50 |
|  |  | Sissy Blalock | Youth Group | 1.50 |
|  | Total Other Hours | 7.50 |

Summary of Adult Hours

| Car Wash | 36.25 |
| --- | --- |
| Bench Assembly | 51.50 |
| Court Yard | 101.50 |
| Other | 7.50 |
| Total Project Hours | 196.75 |

Attachment K   – Flower Box Design

All lumber is pressure treated lumber

Item		Dimension		Quantity

A   	4x4 x 41 	8

B   	4x4 x 48	6

C   	4x4 x 96	8

D   	4x4 x 89	6

E   	5/4x6 x 96	2

F   	5/4x6 x 48	2

5” Galvanized Spikes	49

Step-by-Step instructions

25 8ft 4x4 posted are required for the plant box.

- Pre-cut all component parts of flower box.

- Pre-drill holes in 4x4’s for spikes

- Pre-cut 5/4 board cap for flower box

- Sand all parts and stain

- Nail 4x4 posts together to form box using 5” spikes

- Screw 5/4 board top to box using deck screws

Attachment L  – Final location of benches and Flower Box

Attachment M  – Pictures of Project

Statement of Ambitions and Life Purpose

In the short term it is my ambition to graduate high school.  Then to get into college and earn a degree in computer science.  After graduation I want to get married and have lots of Boy Scouts.

(This is not really sufficient for this section.  In your write-up this section should be a half a page or more.  What do you want to be when you grow up?  What do you want to do with your life?  Write what it is today.  I guarantee it will chance in a few years.)

Positions held in religious institutions, school, camp, community, or other organization in which leadership skills were demonstrated.

Sargent at Arms 		Key Club

Secretary			JR. Kennesaw Beautification League

Captain			Kennesaw Mountain High School Track Team

Director			Chess Club

List awards or honors received during the above service.

Bravery Award		Breaking up fight during heated chess match

Golden Bag Award	Most trash collected in day at a Kennesaw Beautification meeting

# Text boxes

This proposed project is to build eight benches and landscape around those benches in the courtyard of No Creek Baptist Church

No Creek Baptist Church

(770) 555 - 1234

123 Main St

Kennesaw

Ga

30144

This project will benefit the congregation of the No Creek Baptist Church.  The area where the benches will be placed is a courtyard in the middle of the church.  A lot of activities are held in this area and there are never enough places to sit.  These benches will provide additional outdoor seating when the church has activities in this area.  The landscaping that is to be done around the benches will make the area a little more attractive.  Also, the pastor, Rev. Amen, requested the project.

Rev. Ronald Amen

Representative’s Name

Pastor

Representative’s Title

12/1/00

Date of Meeting

(770) 555-6000

Phone No.

Approval Signatures for Project Plan

Project plans were reviewed and approved by

_____________________________              ____________________________

Religious institution, school, or community representative	Date		Scoutmaster/Coach/Advisor			Date

___________________________________________________________                  	________________________________________________________

Unit Committee member				Date		Council or district advancement committee member	Date

March

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 |
| 4 Distribute tickets to sell | 5 Call church with info about car wash for bulletin | 6 | 7 | 8 | 9 | 10 Gather items needed for car wash |
| 11 | 12 | 13 | 14 Make Posters | 15 | 16 Collect money & tickets | 17 Car wash |
| 18 Purchase & transport lumber. Set lumber up to dry | 19 | 20 | 21 | 22 | 23 | 24 |
| 25 Meet with Youth Group leadership about car wash | 26 | 27 | 28 | 29 | 30 | 31 |

Picture from right door

February

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 18 | 19 Projected Project Approval | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 | 27 | 28 Design & print car wash tickets |  |  |  |

Picture from parking lot

2001

2001

2/18/01

2001

3 ½”

3 ½”

Side Piece (part A on Diagram) 2x6 12 ½

3 ½”

4 ½”

4 ½”

Grayed area is to be removed

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 Set Benches Landscaping Review with Pastor |
| 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 13 Present courtyard to church members Get final sign off from pastor | 14 | 15 | 16 | 17 | 18 | 19 |
| 20 | 21 Turn in final write-up | 22 | 23 | 24 | 25 | 26 |
| 27 | 28 | 29 | 30 | 31 |  |  |

May

April

2001

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 Pre-cut benches & sand components | 4 Sand Components | 5 | 6 | 7 |
| 8 | 9 | 10 Assemble Seats | 11 Assemble Base | 12 | 13 | 14 |
| 15 | 16 | 17 Stain | 18 Stain | 19 | 20 | 21 Transport benches to church |
| 22 | 23 | 24 Purchase & Transport Flowers | 25 | 26 Purchase & transport final materials & supplies | 27 Gather & transport all needed tools | 28 Final Assembly of benches Prep Ground |
| 29 | 30 |  |  |  |  |  |

Picture from rear door

2/19/01

2/19/01

2/22/01

Picture of Girls holding posters

Picture of Girls washing cars

Picture of Girls making posters

Picture stacking lumber

Picture of Flower Box

Picture of putting benches together

Picture of crew cutting benches

Picture of Courtyard

Picture of bench on Nature Trail

Picture of ground prep

Picture of crew setting benches

Picture of planting bushes

Picture of work crews

Picture of Presentation Ceremony